## Bug Summary Report
Bug Summary Report
Bugs |  | 29 | [6 empty] | Prepared By:
Status |  |  |  | Priority
To Do | In Progress | Review | Done | Low | Med | High
0 | 0 | 0 | 10 | 5 | 11 | 13
Bug Title |  |  |  | Frontend / Backend | Priority | Status | Creation Date | URL |  | Sprint
System allows discount amount to exceed the product price |  |  |  | Frontend | High | Done | 2025-07-13 18:50 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-98 |  | None
Very long product description breaks the page layout |  |  |  | Frontend | Low | Done | 2025-07-13 18:44 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-97 |  | None | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/ | SCRUM-98 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-98
System accepts negative product prices during product creation |  |  |  | Frontend | High | Done | 2025-07-13 18:37 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-96 |  | None | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/ | SCRUM-97 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-97
System allows creating multiple products with the same name |  |  |  | Frontend | Med | Done | 2025-07-13 18:31 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-95 |  | None | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/ | SCRUM-96 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-96
System allows applying a discount greater than 100% on a product |  |  |  | Frontend | High | Done | 2025-07-13 18:26 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-94 |  | None | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/ | SCRUM-95 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-95
System allows excessively large numbers in product fields (e.g., Selling Price = 999999999) |  |  |  | Frontend | Med | Done | 2025-07-13 17:24 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-93 |  | None | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/ | SCRUM-94 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-94
System allows negative values in the profit margin field |  |  |  | Frontend | High | Done | 2025-07-13 17:14 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-92 |  | None | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/ | SCRUM-93 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-93
System creates a product with an empty Item SKU field |  |  |  | Backend | High | Done | 2025-07-13 17:05 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-91 |  | None | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/ | SCRUM-92 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-92
System allows the creation of a product with purchase price higher than selling price |  |  |  | Backend | High | Done | 2025-07-13 16:57 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-90 |  | None | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/ | SCRUM-91 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-91
System allows the creation of a product with a 0 EGP purchase price |  |  |  | Frontend | Med | Done | 2025-07-13 16:43 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-89 |  | None | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/ | SCRUM-90 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-90
System allows the creation of a new product with negative stock value |  |  |  | Frontend | High | Done | 2025-07-13 16:35 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-88 |  | None | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/ | SCRUM-89 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-89
System allows applying more than 100% discount on a single product when the total invoice value is still positive |  |  |  | Frontend | High | Done | 2025-07-07 21:00 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-64 |  | None | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/ | SCRUM-88 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-88
Long notes break the invoice layout |  |  |  | Frontend | Low | Done | 2025-07-07 20:51 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-63 |  | None | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/ | SCRUM-64 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-64
System allows applying the same type of tax multiple times to the same product |  |  |  | Backend | Med | Done | 2025-07-07 16:09 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-62 |  | None | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/ | SCRUM-63 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-63
System allows unlimited number of days in "Payment Terms" field |  |  |  | Frontend | Med | Done | 2025-07-07 13:49 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-61 |  | None | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/ | SCRUM-62 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-62
System accepts unrealistically old invoice dates |  |  |  | Frontend | Med | Done | 2025-07-07 10:41 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-60 |  | None | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/ | SCRUM-61 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-61
System allows creating an invoice with issue date earlier than invoice date |  |  |  | Frontend | Low | Done | 2025-07-07 10:25 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-59 |  | None | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/ | SCRUM-60 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-60
System allows creation of duplicate invoice numbers |  |  |  | Frontend | High | Done | 2025-07-07 10:05 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-58 |  | None | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/ | SCRUM-59 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-59
Product actual value doesn't change when changing currency |  |  |  | Frontend | Med | Done | 2025-07-07 05:48 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-56 |  | None | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/ | SCRUM-58 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-58
User can switch back and forth between registration and dashboard pages using browser navigation |  |  |  | Frontend | Low | Done | 2025-06-27 11:58 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-34 |  | None | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/ | SCRUM-56 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-56
The system accepts an infinite number of characters in the password field on the registration page |  |  |  | Frontend | Med | Done | 2025-06-27 10:48 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-33 |  | None | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/ | SCRUM-34 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-34
System doesn't include CAPTCHA on registration page |  |  |  | Frontend | Med | Done | 2025-06-27 10:40 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-32 |  | None | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/ | SCRUM-33 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-33
Inconsistency in the registration UI across different languages |  |  |  | Backend | Low | Done | 2025-06-27 10:30 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-31 |  | None | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/ | SCRUM-32 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-32
System accepts weak password with no digits or special characters |  |  |  | Backend | Med | Done | 2025-06-27 10:22 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-30 |  | None | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/ | SCRUM-31 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-31
System accepts digits more than the maximum in phone number field |  |  |  | Frontend | High | Done | 2025-06-27 10:08 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-29 |  | None | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/ | SCRUM-30 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-30
The system accepts invalid email formats during registration |  |  |  | Frontend | High | Done | 2025-06-27 09:53 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-28 |  | None | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/ | SCRUM-29 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-29
The system allows creating multiple accounts with the same phone number |  |  |  | Frontend | High | Done | 2025-06-27 09:42 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-27 |  | None | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/ | SCRUM-28 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-28
Email verification not sent after successful registration |  |  |  | Frontend | High | Done | 2025-06-27 09:29 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-26 |  | None | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/ | SCRUM-27 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-27
Multiple accounts with the same business name |  |  |  | Backend | Med | Done | 2025-06-27 07:20 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-25 |  | None | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/ | SCRUM-26 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-26
[11 empty] | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/ | SCRUM-25 | https://abdelrahmanahmedd1998-1750559979337.atlassian.net/browse/SCRUM-25

## Sheet2
Frontend
Backend | Low | To Do
| Med | In Progress
| High | Review
Done